## Sheet1
WBS No. | Tasks | Task Duration (Days) | Start Date | End Date | 44998 | 44999 | 45000 | 45001 | 45002 | 45003 | 45004 | 45005 | 45006 | 45007 | 45008 | 45009 | 45010 | 45011 | 45012 | 45013 | 45014 | 45015 | 45016 | 45017 | 45018 | 45019 | 45020 | 45021 | 45022 | 45023 | 45024 | 45025 | 45026 | 45027 | 45028 | 45029 | 45030 | 45031 | 45032 | 45033 | 45034 | 45035 | 45036 | 45037 | 45038 | 45039 | 45040 | 45041 | 45042 | 45043 | 45044 | 45045 | 45046 | 45047 | 45048 | 45049 | 45050 | 45051 | 45052 | 45053 | 45054 | 45055 | 45056 | 45057 | 45058 | 45059 | 45060 | 45061 | 45062 | 45063 | 45064 | 45065 | 45066 | 45067 | 45068 | 45069 | 45070 | 45071 | 45072 | 45073 | 45074 | 45075 | 45076 | 45077 | 45078 | 45079 | 45080 | 45081 | 45082 | 45083 | 45084 | 45085 | 45086 | 45087 | 45088 | 45089 | 45090
1 | Requirement Gathering | 1 | 2023-03-13 | 2023-03-13 | X
2 | System Architecture ( Documentation And High level Business flow) | 3 | 2023-03-14 | 2023-03-16 |  | X | X | X
3 | Login /Signup/register | 10 | 2023-03-17 | 2023-03-31 |  |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
4 | Db Design and Django Single and Multi tenant schema | 10 | 2023-04-03 | 2023-04-14 | [21 empty] | X | X | X | X | X | X | X | X | X | X | X | X
4.1 | 1. Single Tenant- different app different Db |  | 2023-04-03 | 2023-04-07 | [21 empty] | X | X | X | X | X
4.2 | 2. Multi - One Db and different schemas and one app |  | 2023-04-10 | 2023-04-14 | [28 empty] | X | X | X | X | X
5 | Dashboard Skelton Creation | 7 | 2023-04-17 | 2023-04-25 | [35 empty] | X | X | X | X | X | X | X | X | X
6 | User Management- Admin, Clients | 5 | 2023-04-26 | 2023-05-02 | [44 empty] | X | X | X | X | X | X | X
7 | Roles and Permissions | 1 | 2023-05-03 | 2023-04-03
8 | Customised filters, search, Notifications and other Widgets like Calender etc. | 12 | 2023-05-04 | 2023-05-19 | [52 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
9 | Integration of ChartJs. With frontend with backend API | 7 | 2023-05-20 | 2023-05-30 | [68 empty] | X | X | X | X | X | X | X | X | X | X | X
10 | Dockerize | 3 | 2023-05-31 | 2023-06-02 | [79 empty] | X | X | X
11 | Fine-tuning , optimization and Testing | 5 | 2023-06-05 | 2023-06-09 | [84 empty] | X | X | X | X | X
12 | Deploying application on Web/cloud server | 2 | 2023-06-12 | 2023-06-13 | [91 empty] | X | X
| Total Days | 66