## Sheet1
WBS No. | Tasks | Task Duration (Days) | Start Date | End Date | 45005 | 45006 | 45007 | 45008 | 45009 | 45010 | 45011 | 45012 | 45013 | 45014 | 45015 | 45016 | 45017 | 45018 | 45019 | 45020 | 45021 | 45022 | 45023 | 45024 | 45025 | 45026 | 45027 | 45028 | 45029 | 45030 | 45031 | 45032 | 45033 | 45034 | 45035 | 45036 | 45037 | 45038 | 45039 | 45040 | 45041 | 45042 | 45043 | 45044 | 45045 | 45046 | 45047 | 45048 | 45049 | 45050 | 45051 | 45052 | 45053 | 45054 | 45055 | 45056 | 45057 | 45058 | 45059 | 45060 | 45061 | 45062 | 45063 | 45064 | 45065 | 45066 | 45067 | 45068 | 45069 | 45070 | 45071 | 45072 | 45073 | 45074 | 45075 | 45076 | 45077 | 45078 | 45079 | 45080 | 45081 | 45082 | 45083 | 45084 | 45085 | 45086 | 45087 | 45088 | 45089 | 45090 | 45091 | 45092
1 | Requirement Gathering and Setting up the project plan | 2 | 2023-03-20 | 2023-03-21 | X | X
2 | Exploratory data Analysis- Discovery, Exploration and analysis to understand features | 15 | 2023-03-22 | 2023-04-11 |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
3 | Setup of Infra for Model training | 2 | 2023-04-12 | 2023-04-13 | [23 empty] | X | X
4 | Start of development of preliminary recommendation model/baseline model | 7 | 2023-04-14 | 2023-04-24 | [25 empty] | X | X | X | X | X | X | X | X | X | X | X
5 | Completion of preliminary trained Recommendation Model with outputs | 8 | 2023-04-25 | 2023-05-04 | [36 empty] | X | X | X | X | X | X | X | X | X | X
6 | Api Creation and integration with frontend | 7 | 2023-05-05 | 2023-05-15 | [46 empty] | X | X | X | X | X | X | X | X | X | X | X
7 | Integration of ChatGpt | 10 | 2023-05-16 | 2023-05-29 | [57 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X
8 | Emailer | 2 | 2023-05-30 | 2023-05-31 | [71 empty] | X | X
9 | Fine-tuning , optimization and Testing | 7 | 2023-06-01 | 2023-06-11 | [73 empty] | X | X | X | X | X | X | X | X | X | X | X
10 | Deploying application on Web/cloud server | 3 | 2023-06-12 | 2023-06-14 | [84 empty] | X | X | X
| Total Days | 63